## Summary
TalkAM — Production Readiness Report
Generated by automated codebase audit · branch features/michael · 2026-08-22
HARD BLOCKERS — fix before any production build ships
• Android release builds are debug-signed — no keystore / key.properties exists
• App is hardcoded to Environment.development everywhere — no way to build for production; base URLs and Flutterwave key stay on staging/test
• Flutterwave payments hardcoded to isTestMode: true app-wide (ads + session booking + subscriptions)
• Sentry is a dependency with call-sites, but SentryService.initializeApp() is never called — every crash report is silently dropped
• Firebase Crashlytics is a dependency, but CrashlyticsService.onCrash() is never called — no crash telemetry at all
• shorebird.yaml does not exist — the Shorebird code-push check at every app launch has no app_id to check against
• No CI/CD pipeline exists anywhere (no GitHub Actions, Codemagic, Bitrise, Fastlane) — all builds/signing/release are manual
• Auth bearer token is stored in plaintext SharedPreferences, not flutter_secure_storage
NOTABLE GAPS — should fix soon, not launch-blocking on their own
• Ad payments trust the Flutterwave client SDK only — no server-side paymentCallback verification (booking flow has this, ads doesn't)
• iOS missing NSFaceIDUsageDescription (local_auth is used) and ITSAppUsesNonExemptEncryption
• iOS version numbers hardcoded in Info.plist/pbxproj (1.0.2/2) and drifted from pubspec.yaml (1.0.0+1)
• Android ProGuard/R8 minification not wired into the release build type despite proguard-rules.pro existing
• Test coverage is real but thin (~7 unit test files, therapist feature only) and not run in any CI
• Therapist account type is a device-local flag, not a server field — lost on reinstall/new device
• Video call screen has no reconnection handling for a mid-call network drop, no call-quality indicator
• Bottom-nav "calendar" icon is the real My Sessions tab — therapist side is real, consumer side is still hand-picked mock cards
STUBS / NOT IMPLEMENTED
• 2FA Verify — backend-confirmed not working
• Localization is fully scaffolded but dormant — every string is hardcoded English
WHAT'S SOLID
• Auth/onboarding, profile, messaging, therapist clients & notes, sessions, earnings & payouts, notifications, groups, search, push notifications, guest flows — all real, end-to-end, no mock data
• flutter analyze: 0 errors on the current branch (370 warnings / 367 info, all style-level)
Full itemized findings are on the "Full Report" tab.

## Full Report
Category | Item | Status | Evidence / Details | Recommended Action
Build & Release | Android release signing | Blocker | build.gradle defines signingConfigs.release but buildTypes.release explicitly points at signingConfigs.debug (code comment: "Signing with the debug keys for now"). No key.properties or .jks anywhere in the repo. | Generate a release keystore, add key.properties (gitignored), wire it into buildTypes.release before any Play Store upload.
Build & Release | Environment switching (dev vs prod) | Blocker | main.dart hardcodes Environment.development. UrlConfig.environment (the field that actually selects base URLs) defaults to development and is never reassigned anywhere in the codebase. No build flavors / no main_prod.dart. | Add a production entrypoint (main_prod.dart) or flavor mechanism that sets Environment.production before a real release build.
Build & Release | Flutterwave test/live mode | Blocker | isTestMode: true is hardcoded in flutterwave_payment_helper.dart — affects every Flutterwave charge app-wide (ad payments, session bookings, subscriptions), not just one flow. | Make isTestMode environment-driven (tie to UrlConfig.environment) so it flips to live automatically in production builds.
Build & Release | Crash reporting — Sentry | Blocker | sentry_flutter is a dependency with real call-sites (SentryService.captureException used in network_service.dart, pay_service.dart) but SentryService.initializeApp() is never called anywhere. Every capture call is a silent no-op. | Call SentryService.initializeApp(...) during app startup (app_config.dart) with the real DSN.
Build & Release | Crash reporting — Crashlytics | Blocker | firebase_crashlytics is a dependency with a CrashlyticsService.onCrash() wrapper that is never invoked. runZonedGuarded only logs locally, doesn't forward to Crashlytics or Sentry. | Call CrashlyticsService.onCrash() at startup and route FlutterError.onError / runZonedGuarded errors to it.
Build & Release | Firebase Analytics | Gap | FirebaseAnalyticsObserver exists (lib/core/services/firebase/analytics.dart) but its usage in routes.dart is commented out — no screen-view or event tracking currently active. | Re-enable the analytics observer once ready to track real usage.
Build & Release | Shorebird code push | Blocker | shorebird_code_push is a dependency and AppConfig._checkForUpdates() calls ShorebirdUpdater() on every launch, but shorebird.yaml does not exist anywhere in the repo (not even a placeholder). The check will fail/no-op silently. | Run `shorebird init` to generate a real shorebird.yaml with the app's real app_id, or remove the dependency if code push isn't planned yet.
Build & Release | CI/CD pipeline | Blocker | Zero CI/CD configuration anywhere in the repo — no .github/workflows, codemagic.yaml, bitrise.yml, .gitlab-ci.yml, Jenkinsfile, or fastlane/. All builds, signing, and store uploads are currently manual. | Set up Codemagic (or equivalent) — user has already been walked through this separately for iOS TestFlight.
Build & Release | Logging level in production | Gap | The global logger is hardcoded to Level.debug in injector.dart with no environment-based gating. Verbose logs (including some access-token logging in auth_repository_impl.dart, gated only by the package's DevelopmentFilter which strips in release builds) may still be broader than intended. | Confirm/tighten log level per build mode; avoid logging tokens or full API payloads even in debug.
Build & Release | Android manifest / build config hygiene | Gap | namespace is still the Flutter default "com.example.talkam" (cosmetic mismatch vs. applicationId "com.talkamtech.app"). ProGuard/R8 (minifyEnabled/shrinkResources) is not wired into buildTypes.release despite proguard-rules.pro existing. | Fix the namespace for consistency; enable minification for smaller/harder-to-reverse release builds.
Build & Release | iOS Info.plist permissions | Gap | Camera/Microphone/Photo Library/Location usage descriptions are present. Missing: NSFaceIDUsageDescription (local_auth/biometric login is used) and ITSAppUsesNonExemptEncryption (required or App Store Connect prompts on every upload). | Add both keys before the first App Store Connect upload.
Build & Release | iOS version number drift | Gap | Info.plist and project.pbxproj hardcode CFBundleShortVersionString/MARKETING_VERSION = 1.0.2 and build number = 2 as literals, instead of $(FLUTTER_BUILD_NAME)/$(FLUTTER_BUILD_NUMBER) — while pubspec.yaml still says 1.0.0+1. flutter build ipa will not sync these. | Switch iOS build settings to reference the Flutter-provided build name/number variables, or manually keep them in sync with pubspec.yaml on every release.
Build & Release | App icon | Done | Real branded 649×675 PNG configured for both Android and iOS via flutter_launcher_icons. | —
Build & Release | Splash screen | Gap | flutter_native_splash only configures a solid background color (#1A6A73) — no branded splash image/logo is set (the image/background_image/android_12 keys are commented out). | Add a branded splash image before launch, or accept the solid-color splash as a deliberate choice.
Build & Release | Privacy policy | Done | Real URL wired app-wide and an in-app PrivacyPolicyScreen fetches content from the backend — not a placeholder. (Minor: double-check the literal "&" in the URL resolves correctly.) | —
Build & Release | Changelog / release notes | Gap | No CHANGELOG.md or release-notes file anywhere in the repo. | Low priority — add before first public release if you want a public changelog.
Security | Auth token storage | Blocker | SessionManager stores the bearer auth token in plain SharedPreferences (unencrypted on-device). flutter_secure_storage IS initialized in the app but is only used for a biometric passcode value, not the actual session token that authenticates every API call. | Move the auth token (and any other session secrets) to flutter_secure_storage.
Security | Hardcoded Google Maps API key | Gap | A Google Maps API key is hardcoded directly in android/app/src/main/AndroidManifest.xml rather than templated via dart-define. Anyone decompiling the APK can extract and reuse it if it isn't restricted. | Verify the key is restricted by package name + SHA-1 fingerprint in Google Cloud Console; consider moving it to a build-time secret regardless.
Security | Dead TLS-bypass code | Cleanup | network_permission.dart defines CustomHttpOverrides with badCertificateCallback => true (accepts any TLS certificate). It's not currently wired up (HttpOverrides.global is never set to it) so it's inert today, but it's a landmine if someone activates it for debugging and forgets to remove it. | Delete the file entirely — there's no legitimate reason to keep dead cert-bypass code in the repo.
Security | Certificate pinning | Gap | No certificate pinning anywhere. Acceptable for a v1 app but worth planning for a later hardening pass. | Consider adding pinning in a future security pass, not launch-blocking.
Security | Hardcoded secrets in source | Done | No hardcoded backend API keys, passwords, or bearer tokens found in lib/. All 3rd-party secrets (Stripe, Flutterwave, Dojah, Face++, Agora) are injected via String.fromEnvironment. Firebase AIza-prefixed keys are committed but are non-secret project identifiers, which is normal. | —
Security | Debug print() statements | Gap | 9 raw print() calls remain across pusher/network/messaging/notification services (not the gated logger package). None print obviously sensitive values, but they're not build-mode-gated. | Swap the remaining print() calls for the logger package for consistency.
Security | Scratch files committed to git | Cleanup | analyze_errors.txt (776 lines) and analyze_errors2.txt (770 lines) — stale `flutter analyze` dumps — are committed at the repo root. Per CLAUDE.md these are explicitly not a maintained baseline. | Delete both and add to .gitignore if they're regenerated locally.
Security | Silent error swallowing | Gap | Only 2 genuinely silent catch (_) {} blocks found (splash_screen.dart, data_privacy_screen.dart) — both deliberate best-effort fallbacks, not bugs, but neither reports to Sentry, so a real regression there would be invisible in telemetry. | Low priority — add a log/Sentry breadcrumb even to intentional fallback catches.
Code Quality | flutter analyze baseline | Done | 0 errors at error severity on the current branch. 370 warnings / 367 info — all style-level (unused imports, null-aware operator nits, duplicate imports), not functional bugs. | —
Code Quality | Automated test coverage | Gap | 7 real unit test files (~1,072 lines) exist, covering narrow areas (tab bar, time-select sheet, thousands formatter, therapist availability/session-rate/profile-store). No integration tests, no golden tests, and — since there's no CI — none of them run automatically on push/PR. | Wire `flutter test` into CI as a cheap first step even before writing more tests; expand coverage to auth/payments/messaging over time.
Code Quality | Lint configuration | Gap | Stock flutter_lints with no project-specific rules added. | Optional — add stricter rules (e.g. avoid_print, prefer_const) if tightening code quality further.
Features | Authentication & onboarding (member + therapist) | Done | Full sign-up → OTP verify → interests → home flow is real end-to-end for both paths, including the full 6-step therapist application wizard. No stub steps found. | —
Features | Profile (edit / notifications / privacy / payment methods / data export / delete account) | Done | All implemented against real v2 endpoints this session, avatar upload included. | —
Features | Messaging | Done | Real v2 conversations, sending, starting new conversations. No mock fallback remains. | —
Features | Therapist clients, session notes, sessions list, notes library, own profile | Done | All real, implemented this session against documented v2 endpoints. | —
Features | Earnings & payouts | Done | Real dashboard/transactions/withdraw/payout-status flow, with clearly-flagged dummy elements only where no backing endpoint exists (BVN line, sample bank card). | —
Features | Notifications | Done | List/mark-all/clear-all/status/session-request accept-decline/report-user all real and wired this session. | —
Features | Side drawer | Done | Real aggregate GET /user/drawer wiring — profile, follow counts, topics, groups, private groups. | —
Features | Groups (explore / recent / my groups / posts / members) | Done | All real as of this session's mock-data removal pass; "Recent" tab newly wired to GET /user/recents/fetch?sort=group. | —
Features | Search (posts / people / groups) | Done | All three tabs wired to real cubits/repositories with pagination and real recent/trending suggestions. | —
Features | Guest / anonymous user flows | Done | GuestUserHelper.handleGuestUserAction consistently gates 25+ screens; no broken guest paths found. | —
Features | Push notifications | Gap | Foreground/background/terminated/tap-to-deep-link states are all wired. Caveat: several session-related notification subtypes (reschedule requested/accepted/declined, cancelled, reminder, therapist-acknowledged) collapse into one generic backend type and can only deep-link to the sessions list, not the specific session. | Backend would need distinct notification types per event to deep-link precisely; otherwise cosmetic.
Features | Video/voice call screen (Agora) | Gap | Real implementation with mic/camera/speaker controls, join/leave lifecycle, and one-shot recovery for a known Agora error. Gaps: no handling for a genuine mid-call network drop/reconnect, no call-quality indicator, no recording/transcript. | Add reconnection handling before heavy production usage — dropped calls with no recovery path is a real support-ticket generator.
Features | Ad payment verification | Gap | The ads payment flow trusts the Flutterwave client SDK's success response only — unlike the booking flow, it never calls the server-side paymentCallback to verify the charge actually landed. The verification call exists in code but is commented out/unused. | Wire the same server-side verification the booking flow already has before ads go live with real money.
Features | Therapist account-type flag | Gap | SessionManager.instance.isTherapistAccount is a device-local SharedPreferences bool, not a server field. TalkamUser.role exists but nothing populates or reads it — therapist status is lost on reinstall or a new device. | Move this to a real server-side user field when the backend supports it.
Features | "Calendar" bottom-nav icon — actually My Sessions | Gap | Correction: this nav slot is not a missing feature. It routes to the real SessionsScreen (/sessionScreen, _kSessionBranch in base_page.dart) — the therapist side was fully rewired to real GET /therapist/sessions data this session. The consumer side, however, is still driven by a hand-picked mock layout (only ever shows two cards, per the screen's own code comment). | Wire the consumer-facing side of SessionsScreen to real booking data the same way the therapist side was done this session.
Features | "Wellness" bottom-nav icon (brain) — actually the Therapist tab | Done | Correction: this nav slot is not a missing feature either. For a therapist it routes to the real ClientsScreen; for a regular user it routes to the real TherapistsListScreen (the patient-facing therapist directory) — both already real, already counted under "Therapist clients, session notes..." above. Separately, a literal lib/features/wellness/wellness_screen.dart file exists with a static "Coming soon" EmptyState, but it has zero references from any route or nav entry anywhere in the app — genuinely orphaned dead code, unrelated to the live bottom nav. | Delete the orphaned wellness_screen.dart, or repurpose it if a real wellness feature is planned later — it is not currently reachable by any user.
Features | 2FA Verify | Not Implemented | Backend team confirmed this endpoint is "not working for now" when it was wired up earlier this session. | Follow up with backend on real status before enabling in the UI.
Features | Localization | Not Implemented | Fully scaffolded (l10n.dart, intl_en.arb, flutter_intl enabled) but entirely dormant — localization_extension.dart is commented out and MaterialApp registers no S.delegate. Every string is hardcoded English. | Decide if multi-language support is actually on the roadmap; if not, consider removing the dead scaffold.
Features | Dark theme | Not Implemented | AppTheme.darkTheme exists but the app never switches to it — light-only in practice. | Low priority unless dark mode is a stated requirement.
Features | Post composer formatting tools | Not Implemented | Text-style, GIF, and bulleted-list buttons in the create-post and reply composers all just toast "Coming soon"; only image attachment works. | Either implement or remove the buttons so they don't look broken.
Features | Poll widget | Not Implemented | PostPollWidget renders a raw debug Placeholder(). Currently unreferenced/dead code, so not user-visible, but has no real UI if ever wired up. | Build real UI before enabling polls, or delete the dead widget.
Features | Group member "Follow" button | Not Implemented | The Follow button on a group member row is a no-op ("Visual mock" per its own code comment). | Wire to the real follow-toggle endpoint already used elsewhere, or remove the button.
Features | Group rules tab | Not Implemented | Always renders 4 hardcoded fake "Rule N: Be Respectful" entries regardless of the actual group — not real per-group data. | Wire to the real group guidelines endpoint (already used elsewhere in the app).
Tech Debt (self-noted) | Refactor post details page | Gap | Tracked in the repo root's `todo` file as outstanding. | Prioritize per team roadmap.
Tech Debt (self-noted) | Refactor chat screen | Gap | Tracked in the repo root's `todo` file as outstanding. | Prioritize per team roadmap.
Tech Debt (self-noted) | Move hardcoded URLs to Remote Config | Gap | Tracked in the repo root's `todo` file as outstanding. | Prioritize per team roadmap.